## Sheet1
OrderID | ProductName | ProductType | Quantity | Priority | CustomerName | OrderDate | DueDate | EstimatedHours | Status | AssignedLine | Progress | Dependencies | Notes
ORD-2025-001 | Widget Pro X1 | Electronics | 500 | High | TechCorp Inc | 2025-07-25 | 2025-08-10 | 12.5 | Scheduled | LINE-C01 | 0 |  | Standard production
ORD-2025-002 | Circuit Board CB-400 | Electronics | 1200 | Medium | ElectroMax Ltd | 2025-07-26 | 2025-08-15 | 28.8 | In Progress | LINE-A01 | 35 |  | Complex PCB layout
ORD-2025-003 | Automotive Part AP-250 | Automotive | 300 | Critical | AutoParts Pro | 2025-07-24 | 2025-08-05 | 15 | Scheduled | LINE-C01 | 15 | ORD-2025-001 | URGENT - Customer escalation
ORD-2025-004 | Medical Device MD-100 | Medical | 150 | High | MedDevice Solutions | 2025-07-27 | 2025-08-12 | 7.5 | Scheduled | LINE-C01 | 0 |  | FDA compliance required
ORD-2025-005 | Package Set PS-50 | Package | 2000 | Low | PackageCorp | 2025-07-28 | 2025-08-20 | 24 | Scheduled | LINE-C01 | 0 | ORD-2025-002 | Bulk order
ORD-2025-006 | Heavy Component HC-75 | Heavy | 80 | Medium | HeavyIndustry Co | 2025-07-25 | 2025-08-08 | 4 | In Progress | LINE-B02 | 60 |  | Special tooling needed
ORD-2025-007 | Precision Tool PT-200 | Precision | 250 | High | PrecisionTech | 2025-07-27 | 2025-08-11 | 10 | Scheduled | LINE-C02 | 0 | ORD-2025-003 | High precision required
ORD-2025-008 | Electronic Module EM-300 | Electronics | 800 | Medium | ModuleMakers | 2025-07-28 | 2025-08-18 | 20 | Scheduled | LINE-C02 | 0 | ORD-2025-004 | New product launch
ORD-2025-009 | Bebe-0911-Rody | Medical | 1793 | Low | Enache Boris | 2025-07-29 | 2025-08-12 | 65.5 | Scheduled | LINE-C02 | 0
ORD-2025-010 | Bebe-09000 | Medical | 2396 | Medium | Boris | 2025-07-29 | 2025-08-12 | 8 | Scheduled | LINE-A02 | 0
ORD-2025-011 | BAMBY | Heavy | 4068 | Low | POPO | 2025-07-29 | 2025-08-12 | 8 | Planned |  | 0 |  | IOIOIOOOO